AGREEMENT BETWEEN IEA AND THE MINISTRY OF EDUCATION AND SCIENCE OF THE REPUBLIC OF LATVIA ABOUT THE PARTICIPATION IN THE PIRLS 2016 STUDY

The Ministry of Education and Science of the Republic of Latvia, represented by the minister for education and science Mr. Kārlis Šadurskis, address: Vaļņu iela 2, Riga, LV-1050, Latvia, referred to as Latvia on the one part,

and

The International Association for the Evaluation of Educational Achievement (Chamber of Commerce The Hague # 41158871 – VAT not applicable), acting by and through Dr Dirk Hastedt, Executive Director, referred to as IEA

HAVE AGREED

The participation of Latvia in the PIRLS 2016 (Grade 4) assessment, including the calculation of the international scores and the publication of the data.

ARTICLE I – PURPOSE OF THE CONTRACT – DURATION

RELATION OF WORKS TO BE DONE BY THE IEA, or IEA WITH THE COLLABORATION OF LATVIA DURING THE PIRLS 2016 PROJECT

2015 – Development

- framework and specifications update

- selecting new passages for reading test

- developing the replacement items and scoring procedures for those items

- field test of instruments

- revising and streamlining the questionnaires (for student, teacher, parents and school), preparing them for field testing

- developing the procedures for instruments translation verification

- developing sampling plans, monitoring the sampling procedures

- developing operations and data collection manuals, and training countries in field test data collection and scoring procedures

- managing field test instruments translation verification

- conducting field test data analysis

- preparing final version of the survey instruments

2016 – Main Survey

- developing operations and data collection manuals, and training countries in main survey data collection and scoring procedures

- managing main survey instruments translation verification

- training Quality Control Monitors, conducting quality assurance site visits during data collection, and documenting the results

- constructing an international database and checking and rechecking the accuracy and comparability of the national datasets

2017 – Reporting

- conducting a variety of data analyses, including scaling, estimating sampling error, and deriving variables for reporting

- preparing report tables and having them reviewed by the participating countries

- writing and publishing the international and technical reports

- producing a thoroughly documented database and accompanying PIRLS User's Guide

- conducting training seminar in using PIRLS database

ARTICLE 2 – ROLE OF THE BENEFICIARIES

Latvia has the rights on the results of the study executed according the Agreement within the scope of agreements accepted by IEA and the participating countries.

IEA has the right to evaluate the data collected to meet IEA quality standards.

Latvia is responsible for:

- delivering necessary information for performing the study to IEA according to the project time schedule.

- accepting the results of the study executed according to the Agreement and to pay the participation fees.

ARTICLE 3 – BREAKDOWN OF COSTS – FINANCING THE ACTION

The total participation fee for Latvia for one grade level amounts to USD 100,000 (one hundred thousand US dollars) plus EUR 100,000 (one hundred thousand EUR), payable in 2016.

ARTICLE 4 – PAYMENT ARRANGEMENTS

The annual participation fees are payable free of charge, within 30 days to: Stichting IEA Secretariaat The Netherlands; ABN-AMRO bank, Singel 548, 1017AZ Amsterdam – The Netherlands (SWIFT/BIC code: ABNANL2A):

USD account number 48.19.62.069 – (IBAN: NL52ABNA0481962069) and

EURO account number 48.19.61.968 – (IBAN: NL63ABNA0481961968).

ARTICLE 5 – SUBMISSION OF REPORTS AND OTHER PUBLICATION

The International Report PIRLS 2016 will be provided December 2017 and the International database will be made available May 2018.

This contract has been executed on _____________

Signed for and on behalf of the Ministry of Education and Science of the Republic of Latvia by the minister for education and science Kārlis Šadurskis

-------------------------------------

Signed for and on behalf of

The International Association for the Evaluation of Educational Achievement

by Dirk Hastedt (Executive Director)

-----------------------------------